## Summary
GROZA Development Breakdown & Cost Calculator
Hourly Rate (€): | 100
Stage | Category | Hours | Cost
POC (Proof of Concept) |  | 400
| Wireframes & Design | 40
| Authentication & Authorization | 60
| Company Management (Basic) | 80
| CASE Management (Basic) | 60
| QR Code Generation | 40
| QR Validation (Basic) | 40
| Basic Dashboard | 40
| Testing & Bug Fixes | 40
MVP (Minimum Viable Product) |  | 700
| Enhanced UI/UX | 80
| Company Onboarding Flow | 60
| Employee & Vehicle Management | 80
| Document Upload & Storage | 60
| Permit Generation (Auto) | 100
| DSP Manual Approval | 80
| Enhanced QR Validation | 60
| Notifications System | 60
| Audit Logs | 40
| Testing & QA | 80
Full Product |  | 1420
| Inspector Dashboard & Reports | 120
| Advanced Analytics | 100
| Change Request Workflow | 80
| Multi-tenant Architecture | 120
| Document OCR & Auto-extraction | 160
| Mobile App (iOS/Android) | 400
| Advanced Security & Compliance | 80
| Performance Optimization | 80
| Comprehensive Testing | 120
| Documentation & Training | 80
| Deployment & DevOps | 80
TOTAL

## Detailed Breakdown
GROZA - Detailed Development Stages
POC (Proof of Concept)
Goal: | Validate core concept with clickable wireframes and basic functionality
Scope:
• Basic authentication (login/logout)
• Simple company registration
• Create CASE with minimal data
• Generate QR code for CASE
• Scan QR and validate company status
• Role-based dashboards (static)
• No document upload
• No approval workflows
• Mock data for testing
Deliverables:
• Clickable wireframes (Figma/Penpot)
• Working prototype with core flows
• Basic database schema
MVP (Minimum Viable Product)
Goal: | Production-ready core features for initial rollout
Scope:
• Complete authentication & user management
• Company onboarding with approval workflow
• Employee & vehicle management
• Document upload & validation
• Automatic permit generation (transport, mortuary passport)
• DSP manual approval for embalming permits
• Enhanced QR validation with all checks
• Email notifications
• Audit logs for all actions
• Company status management (GREEN/RED)
• Basic reporting
Deliverables:
• Production-ready web application
• All core workflows functional
• User documentation
• Deployed on staging/production
Full Product
Goal: | Complete platform with advanced features and mobile support
Scope:
• Inspector dashboard with advanced analytics
• Exportable reports (PDF, Excel)
• Company change request workflow
• Multi-tenant architecture
• OCR for document auto-extraction
• Mobile apps (iOS & Android) for validators
• Advanced security (2FA, audit logs)
• Performance optimization for scale
• Comprehensive testing & QA
• Complete documentation
• Training materials
• CI/CD pipeline
Deliverables:
• Complete web platform
• iOS & Android mobile apps
• Admin & user documentation
• Training materials & videos
• Production deployment

## Stage Comparison
Development Stage Comparison
Aspect | POC | MVP | Full Product
Timeline | 4-6 weeks | 3-4 months | 8-12 months
Team Size | 1-2 developers | 3-4 developers | 5-8 developers
Users | Internal testing only | 50-100 users | Unlimited
Features | 20% core features | 80% core features | 100% all features
Testing | Basic manual testing | QA + automated tests | Comprehensive QA
Documentation | Minimal | User guides | Complete docs + training
Mobile Support | None | Responsive web | Native iOS/Android
Scalability | Single server | Basic scaling | Enterprise-grade
Security | Basic auth | Production security | Advanced security
Support | None | Basic support | Full support + SLA